## Pre
PRE - CONFERENCE
START
TASK | CONTACT
Determine, apply and obtain sponsorship from all applicable IEEE and/or non-IEEE organizational units | Contact SPS Conference Services Staff
36-24 Months
TASK | CONTACT
Register your conference with IEEE | IEEE Conference Application
Submit MOU/FaMOU (if applicable) | Click for more information on MoU/FaMoU
Complete POBC/COI Forms
Submit IEEE Conference Publication Form | IEEE Conference Publication Form
Establish IEEE Concentration Bank Account | Contact Conference Finance
Submit Budget to IEEE OU for review and approval | SPS Budget Template
Issue Request for Proposal (RFP) and contract Management Company | IEEE Templates: Contract Legal Documents
Site reconfirmation and finalizing contract for submission to IEEE SPS
Contact local IEEE Section for support
18-15 Months
TASK | CONTACT
Begin outreach to eductational institutions, corporations, government and industry support and patronage
Apply for grants for conference support
Submit advertisement for IEEE SP Magazine | Contact SPS Conference Services Staff
Develop technical program, establish paper submission process and deadlines. Submisison process should include | IEEE Conference Peer Review Service Network
Contact IPR Office
Set-up online paper managemet sytem
Draft a Call for Papers (CFP) | Promotional Event/Flyer Templates
15-12 Months
Register for (optional) | Contact IEEE eXpress
Issue Call for Papers (CFP) and exhbit prospectus at current year's conference, if applicable
Meet/Discuss with previous years committee best practices
12-9 Months
Promote Call for Papers | Submit to SPS Conference Services Staff
Submit revised budget (incl. updates to projected attendance based on paper submission numbers, confirmed financial contributions, expenses, etc.) | Submit to SPS Conference Services Staff
Review and reconfirm hotel meeting space and room block
9-6 Months
Create registration form and ensure registration service Payment Card Industry (PCI) compliant.
Submit revised budget (incl. updates to projected attendance based on paper acceptance numbers confirmed financial contributions, expenses, etc.)
Seek approval on registration fees from VP- Finance and VP-Conferences before they are announed. | Contact SPS Conference Services Staff
6-4 Months
Launch online registration
Complete paper reivew process. Finalize technical program. Notify authors.
Create and publish advanced program
Submit revised budget (incl. updates to projected attendance based on paper acceptance number, confirmed financial contribution, expenses, etc. | Submit to SPS Conference Services Staff
4 Months - START
Prepare, finalize and post event survey | Survey Template - or
Submit Pre-Conference forecast | Submit to SPS Conference Services Staff
Issue travel grants, if applicable
Collect copyright forms for posting content on SigView
Monitor Budget
IEEE Signal Processing Society
Conference Timeline

## Post
POST - CONFERENCE
Immediately After Conference
Notify authors of non-presented papers for the appeals process
Issue post event survey, if applicable SPS Staff will issue on the conference's behalf
Post photos and notices of appreciation on the website
Send recorded content of keynotes, tutorials, special sessions to SigView for posting | Contact Chief Editor of SigView
1 Month Post
TASK | CONTACT
Repay IEEE SPS advance loans within 30 days from the end date of the conference, if applicable
Conclude the non-presented paper ushto appeals process
Submit Conference Proceedings/Content (Xplore CD and other media types) per LoA | Contact IEEE Conference Services
Submit Post Conference budget | Submit to SPS Conference Services Staff
3 Months Post
Distribute surplus | See Conference Closing Checklist
Close conference bank account and submit proof of account closure
Submit final financial report with Certificate of Accuracy | See Conference Closing Checklist
4-5 Months Post
Prepare and submit all audit material to independent auditor | See Conference Closing Checklist
Submit final financial report with Certificate of Accuracy | See Conference Closing Checklist
6 Months Post
Submit final financial report with Certificate of Accuracy | See Conference Closing Checklist
IEEE Signal Processing Society
Conference Timeline